## Admin Panel
Vaani 2.0 Admin Panel Tracker Sheet
Feature | SubFeatures | Status | Date | Est. Start Date | Est. End Date
Admin Dashboard
| Call Monitoring | Completed | 2022-01-15
| Channel Monitoring | Completed | 2022-01-11
| Hourly Campaign Report | Completed | 2022-08-05 |  | 2022-07-30
| Client Wise Monitoring | In Progress |  |  | 2022-09-09
Client Creation
| Creation | Completed | 2021-12-10
| Edit | Completed | 2021-12-10
| Delete | Completed | 2021-12-10
Role Creation
| Hierarchical Structure | Completed | 2021-12-17
| Edit | Completed | 2021-12-17
| Delete | Completed | 2021-12-17
DNI Creation
| Client Wise DNI Creation | Completed | 2022-01-10
| Edit | Completed | 2022-01-10
| Delete | Completed | 2022-01-10
| With Range/Single DNI | Completed | 2022-01-11
Campaign Creation
| Add List & Update - Inbound | Completed | 2021-12-25
| Add List & Update - Outbound | Completed | 2022-05-02
| Crm Fields | Completed | 2022-04-29
| Lead Upload | Completed | 2022-05-03
| Batches (Active with filters/Inactive) | Completed | 2022-05-05
| Rechurn Dispositions | In Progress |  |  | 2022-06-23
| Call Windows | Completed | 2022-02-22
| Breaks | Completed | 2022-02-25
User Creation
| Role Wise User Creation | Completed | 2021-12-16
| Edit | Completed | 2021-12-16
| Delete | Completed | 2021-12-16
Role Wise Access
| System Default Access | WIP | 2022-07-30
| Client Wise Access | WIP | 2022-07-30
Dynamic Menu Creation
| Default Menu | Completed | 2022-02-15
| Client Wise Menu Creation | Completed | 2022-02-17
Reports
| Inbound | Completed | 2022-07-29 |  | 2022-07-31
| Outbound | Completed | 2022-07-29 |  | 2022-07-31
Multi-Tenancy |  | Completed | 2022-04-18
PBX Configuration |  | Completed | 2022-01-20
Feature Wise Access |  | In Progress |  |  | 2022-07-30
Admin can logout agent |  | Completed | 2022-07-04 | 2022-07-04 | 2022-07-06
Action log module |  | Pending |  | 2022-10-10 | 2022-10-14
Disposition (Multilevel disposition) |  | Completed | 2022-06-22
Change Password |  | Completed | 2022-06-23
Hold Music |  | Completed | 2022-06-27 |  | 2022-06-24
sound File |  | Completed | 2022-07-19 | 2022-06-27 | 2022-07-25
CRM Module configuration |  | Pending | Yet to be started

## Agent Panel
Vaani 2.0 Agnet Panel Tracker Sheet
SR No | Module | SubAction | Status | Start Date | End Date
1 | Agent Login | Login history | completed | 2021-11-23 | 2021-11-26
|  | SIP connection | completed | 2021-11-26 | 2021-11-30
|  | Campaign selection | completed | 2022-01-21 | 2022-02-13
2 | Agent Dashboard | Agent Daily login detail | completed | 2022-01-04 | 2022-02-16
|  | Agent Daily login detail | 2022-08-05 | 2022-02-25 | 2022-03-14
|  | Search lead | completed | 2022-03-14 | 2022-09-09
3 | Agent Dialer Actions | Ready / Pause | completed | 2022-01-04 | 2022-01-04
|  | manual dial display | completed | 2022-01-04 | 2022-01-10
|  | Call Action history | completed | 2022-01-11 | 2022-01-18
|  | manual dial hold | completed | 2022-01-11 | 2022-01-13
|  | manual dial transfer | completed | 2022-01-13 | 2022-01-27
|  | manual dial confrence | completed | 2022-01-13 | 2022-01-27
|  | manual dial consult | completed | 2022-01-13 | 2022-01-27
|  | inbound call display | completed | 2022-01-28 | 2022-02-01
|  | inbound call confrence | completed | 2022-02-01 | 2022-02-24
|  | inbound call transfer | completed | 2022-02-01 | 2022-02-24
|  | inbound call hold | completed | 2022-02-01 | 2022-02-01
|  | inbound call consult | completed | 2022-02-01 | 2022-02-24
|  | outbound call display | completed | 2022-04-15 | 2022-04-20
|  | outbound call confrence | completed | 2022-04-20 | 2022-05-11
|  | outbound call transfer | completed | 2022-04-20 | 2022-05-11
|  | outbound call hold | completed | 2022-04-20 | 2022-05-11
|  | outbound call consult | completed | 2022-04-20 | 2022-05-11
4 | Agent Tenant DB | All activity | completed | 2022-03-30 | 2022-04-14
5 | Outbound | preview | completed | 2022-05-11 | 2022-05-12
|  | time preview | completed | 2022-05-24 | 2022-05-27
|  | progressive | completed | 2022-05-27 | 2022-06-07
|  | predictive | pending
|  | rechurn | completed | 2022-06-15 | 2022-07-01
2022-07-29
2022-07-29
|  |  |  | 2022-10-10 | 2022-10-14
2022-06-27
2022-07-19

## Telephony
Vaani 2.0 Telephony Tracker Sheet
Features | Sub Features |  | Status | Date | Remark
Agent Login with SIP
| Login Credential Validation |  | Completed | 2021-11-18
| SIP Synchronization with Agent Panel |  | Completed | 2021-11-19
Multiple Campaign Login |  |  | Completed | 2021-11-22
Agent Mode
| Ready |  | Completed | 2021-11-26
| Pause |  | Completed | 2021-11-26
| Break |  | Completed | 2021-11-26
Inbound Call
| Fetching callerid and Display |  | Completed | 2021-11-22
| Call Hangup Feature |  | Completed | 2021-11-22
| Transfer | IN/EXT | Completed | 2022-03-15
| Hold/Unhold |  | Completed | 2022-03-14
| Attend Conference |  | Completed | 2021-11-24
| 3-way Conference |  | Completed | 2021-12-17
| Recording Feature |  | Completed | 2021-12-09
| Ingroup Creation |  | Completed | 2021-12-10
| Call Tranfer Logic |  | Completed | 2021-12-13
Manual Call | Fetching callerid and Display |  | Completed | 2021-12-02
| Dial Feature | IN/EXT | Completed | 2021-12-01
| Call Hangup Feature |  | Completed | 2021-12-02
| Recording Feature |  | Completed | 2021-12-09
| Transfer | IN/EXT | Completed | 2022-03-15
| Attend Conference |  | Completed | 2022-03-14
| 3-way Conference |  | Completed | 20-21-2021
Preview Dialing | Normal Preview |  | Completed | 2022-06-15
| Time Preview |  | Completed | 2022-06-15
Progresive Dialing | Fresh Data Dialing |  | Completed | 2022-06-22
| Rechurn Data Dialing |  | Completed | 2022-07-04
Predictive Dialing | All logic involved in it |  | WIP | 2022-09-01
Auto IVR |  |  | Not Yet Started
Analytics |  |  | Not Yet Started

## Team Member
Name | Desgination | Remarks
Ashish Vishwkarma | PHP Developer
Ravinder Kaur | PHP Developer | Joined on 1st Dec,
Krunal Wankhade | UI Developer | Availaible On Demand
Amit Anand | Manager-Software& Devlopment | Started working from 1st November

## Technology
Technology Used | Language | Team Member
For FrontEnd | PHP 7.3 | Ashish/Ravinder Kaur/Krunal
FrameWork(YII2)
HTML/CSS
JavaScript/Jquery
DB | MySQL 5.6
For BackEnd
| Telephony Asterisk Ver16.22 | Amit Anand
Python 3.6
Perl 5.6
C++13
Bash Scripting